## Sheet1
2020: | 2020: | 2020: | 2020: | 2020:
January | Feburary |  | March | April
Conceptual design | Preliminary design | Decision gate: Review | Detail design and development
Problem definition | Functional analysis |  | Subsystem design | Verification of processes
Need Identification | Trade-off studies |  | Evaluation of alternatives | Development of prototypes
Requirement Analysis | Early prototyping |  | Production planning | Test and evaluation
System/program planning | Contracting
Program implementation
2020: | 2020: | 2020: | 2020: | 2020:
May | June |  | July | August (First half)
Detail design and development |  | Decision gate: Review | Production/construction
Order equipment | Production/constructon |  |  | System assesment
for construction | Construction of physical
system begins.
Support from SW Dev
during installation.
2020: | 2020: | 2020: | 2020: | 2020:
| August (Second half) | September (first half) |  | September (second half)
Milestone: Construction done |  |  | Decision gate: System should | Operational use and system support
| SW testing on client site | Test and evaluation | be complete. (Should production | System operation in user environment
| Acceptance testing |  | and construction be extended?) | Operational testing
2020: | 2020: | 2020: | 2021:
October | November | December | January
Operational use and system support
Field data collection | System modification
and analysis. | for improvement.